## Slide 1: Production of R&R Materials External Vendor Collaboration
R&R Vendor
Excel Translations
HHG*
As of 30May2020
* Activities noted throughout this workflow for HHG also apply when another print vendor is utilized

## Slide 2: AGENDA
Topics of Discussion | Slide Number
Key Stakeholders | 3
Process Overview | 4
R&R Material Development | 5 - 7
Pre-Flight | 8 - 9
Translation | 10 -11
DTP/Final Layout | 12 - 13
Print Production | 14
References | 15-21
Version History | 22

## Slide 3: Key Stakeholders
Bayer R&R Manager
R&R Vendor
Development of English Core Materials)
EXCEL Translations
Country Specific Language translations & DTP for print ready files
HHG/ Print Vendor
Print and Shipping of final approved materials
Bayer CLM
Completes In Country Review (ICR) and prepares ERC submission

## Slide 4: R&R External Vendor Process Overview
R&R Material Development
Vendor KOM
Development of Materials
US-LMR
Pre-Flight
Submit English core PDF files for Pre-Flight
Complete Pre-Flight
Translation
Provide Final and Approved Files for Translation
Complete Translation
1.1
2.1
2.2
3.1
1.2
3.2
Print Production
Complete print production
5.1
DTP/ Final Layout
Provide Files for ERC submission
Prepare print-ready files
4.1
4.2
1.3

## Slide 5: R&R Material Development
1.1
R&R Vendor HHG/ Print Vendor Excel Translations
Bayer R&R Manager
Vendor KOM
Lead Role
Supporting Role
INPUT
R&R strategy & SOW (R&R vendor)
HHG specification rate card items HHG Standard Specifications- Rate Card
Footer naming convention Footer Naming Convention
File naming convention File Naming Convention
ACTIONS
Bayer R&R Manager sets up external vendor KOM
R&R Vendor provides overview of planned materials and timelines for development
HHG will review specifications associated with materials to be developed
HHG will review FTP and requirements:
  Pre-Flight (R&R Vendor)
  Print Ready Delivery (Excel Translations)
Excel Translations will review requirements:
  File transfer (R&R Vendor)
Bayer R&R Manager will review communication pathway including TEAMS structure/utility
OUTPUT
Alignment on HHG specification; completion of
Agreement on timelines
Agreement on communication pathway
Access granted to FTP (HHG and Excel)
TOOLS & SYSTEMS
Microsoft office TEAMs
HHG FTP
Excel FTP

## Slide 6: R&R Material Development
1.2
R&R Vendor
Bayer R&R Manager
Bayer Study Team
Development of R&R Materials
Lead Role
Supporting Role
INPUT
Aligned specifications
Aligned timelines
ACTIONS
R&R Vendor will develop materials in InDesign (unless otherwise informed by Bayer R&R Manager)
  See language suggestions from Excel Translations English Core Localization Friendly Recommendations
  See guidance from Bayer US LMR US LMR Guidance
Bayer R&R and Study Team complete review
OUTPUT
English core files in In Design
TOOLS & SYSTEMS
Microsoft office TEAMs

## Slide 7: R&R Material Development
1.3
R&R Vendor
Bayer R&R Manager
Bayer LMR Administrator
Bayer Study Team
US LMR
Lead Role
Supporting Role
INPUT
Final English Core Files (required for US-LMR)
US LMR Guidance
ACTIONS
R&R vendor/Project Owner should create a placeholder in Veeva/Content Factory in order to have the Project/MA number assigned (this project number is required to be included on final US LMR approved materials). Note: separate project numbers are needed for US English and US Spanish, therefore when US Spanish is needed, a separate placeholder should be created in VEEVA/CF
R&R Vendor sends R&R Manager files to be submitted for US-LMR with all comments/annotations for review and approval prior to submission via Content Factory.
R&R Manager reviews and approves files for submission via Content Factory.
R&R Vendor submits files via Content Factory, by Wednesday’s 3:00 pm US EST in order to be added to the following Friday’s US LMR review.
R&R Vendor will send email to US LMR Administrator (michelle.brotons@bayer.com) and respective R&R Manager confirming upload of all files in Content Factory in order for workflow to be initiated.
Bayer LMR Administrator will provide R&R Manager LMR feedback for review
R&R Manager and Study Team complete review of LMR feedback; R&R Manager communicates changes needed to R&R vendor.
R&R Vendor adapts materials based on US LMR feedback
OUTPUT
US-LMR approved English core files
TOOLS & SYSTEMS
Content Factory

## Slide 8: Pre- Flight
2.1
R&R Vendor
Bayer R&R Manager
HHG
Submit English Core PDF Files for Pre-Flight
Lead Role
Supporting Role
INPUT
Final English high-res print-ready PDFs per HHG print specs (created from final native English files)
HHG pre-flight Instructions HHG FTP & Pre-Flight
Pre-flight checklist Pre-Flight Checklist
ACTIONS
R&R vendor submits files to HHG FTP for pre-flight
  English high-res print-ready PDFs
  Embedded artwork and fonts
  Using file & footer naming convention
R&R vendor works with HHG in case of pre-flight submission failure(s)
R&R vendor sends notification of pre-flight submission (via email or TEAMS as agreed)
  HHG: bayer.clinicaltrials@hhglobal.com
  Bayer R&R Manager
OUTPUT
Confirmed successful pre-flight submission (HHG success emails)
TOOLS & SYSTEMS
Microsoft office TEAMs
HHG FTP
Support: pre-flight.support@hhglobal.com

## Slide 9: Pre- Flight
2.2
HHG
Bayer R&R Manager
R&R Vendor
Complete Pre-Flight
Lead Role
Supporting Role
INPUT
Final Native high resolution English Core files submitted to HHG
HHG pre-flight Instructions HHG FTP & Pre-Flight
Pre-flight checklist Pre-Flight Checklist
ACTIONS
HHG completes pre-flight check
  Preflight passed = ready for next phase (Translation)
  Preflight failed = back to R&R vendor for correction
HHG sends notification confirming completion of pre-flight check (via email or TEAMs)
  R&R vendor
  Bayer R&R Manager
OUTPUT
Notification of pre-flight check completion
TOOLS & SYSTEMS
Microsoft office TEAMs
HHG FTP

## Slide 10: Translation
3.1
R&R Vendor
Bayer R&R Manager
Excel
Provide Final and Approved Files for Translation
Lead Role
Supporting Role
INPUT
Final approved files ready for translation (note: can be done via Teams or uploaded to Excel FTP)
  Final native English Core Files
    High resolution
    Final artwork and fonts
    Using file & footer naming convention
  Pre-flight passed high-res print-ready PDFs (the ones that passed pre-flight)
    Evidence (HHG success emails) of pre-flight passing
HHG pre-flight Instructions HHG FTP & Pre-Flight
ACTIONS
Complete file transfer and hand-off of English Core materials and collaterals (see input)
R&R Vendor sends notification when files have been transferred (via email or TEAMs)
  Excel Translations study Project Manager
  Bayer R&R Manager
OUTPUT
Files transferred to Excel for translations
TOOLS & SYSTEMS
Microsoft office TEAMs
Excel FTP

## Slide 11: Translation
3.2
Excel
Bayer R&R Manager
Complete Translations
Lead Role
Supporting Role
INPUT
English Core materials and collaterals
Comprehensive translation scope from R&R Manager (languages, countries, requirements, specs, etc)
ACTIONS
Excel provides translated files for CLM In-Country Review within Excel FTP
  Excel will follow the English design file as is (including file and footer naming, placement of footers and other page information).
Excel provides pdf files in layout within Excel FTP “CLM Read First”
Excel notifies Bayer R&R Manager when translated files are available
Bayer R&R Manager coordinates ICR with CLMs
US English Core materials provided to Excel Translations with LMR Project/MA Number (MA number)
        Excel Translations will maintain this LMR project/MA on the US English materials and will delete from country translated materials. Additionally, when applicable, Excel will add US Spanish LMR project number to approved materials
          US Spanish: Excel Translations will complete In-Country Review via 3rd linguist and will provide the translation certificate when complete. No need to complete back-translation.
        Note: UK LMR will also produce LMR Project number, CLMs should provide this and request it to be added to UK English LMR materials via the ICR CLM feedback form (or via PDF annotation)
OUTPUT
Excel FTP
  Word files(s) with bi-lingual tables with English + corresponding translations
  CLM/ERC instructions and guidelines + English PDFs (for reference)
TOOLS & SYSTEMS
Microsoft office TEAMs
Excel FTP

## Slide 12: DTP/ Final Layout
4.1
Excel
Bayer R&R Manager
Provides Files for ERC Submission
Lead Role
Supporting Role
INPUT
Completed ICR files & CLM Feedback form
ACTIONS
Excel provides translated, formatted and QA’d files within Excel FTP
  Format: Low resolution pdf
Excel notifies Bayer R&R Manager when files are available
Bayer R&R Manager coordinates ERC review/approval with CLMs
OUTPUT
Excel FTP
  Translated low resolution PDF files for ERC submission
  CLM/ERC instructions and guidelines + English PDFs (for reference
TOOLS & SYSTEMS
Microsoft office TEAMs
Excel FTP

## Slide 13: DTP/ Final Layout
4.1
Excel
Bayer R&R Manager
Prepares Print Ready Files
Lead Role
Supporting Role
INPUT
ERC approved files & CLM ERC Feedback Form
ACTIONS
Excel adapts files based on ERC feedback
Excel uploads print-ready files to HHG FTP upon receipt of official print request from R&R Manager
  Using file naming convention
  High-resolution PDF
Excel sends notification of upload (via email or TEAMS as agreed)
  HHG: bayer.clinicaltrials@hhglobal.com
  Bayer R&R Manager
Excel uploads Translation certificate to Excel FTP
OUTPUT
Excel FTP
  High-res print-ready files uploaded to HHG FTP
TOOLS & SYSTEMS
Microsoft office TEAMs
Excel FTP
HHG FTP

## Slide 14: Print Production
5.1
HHG
Bayer R&R Manager
Complete Print Production
Lead Role
Supporting Role
INPUT
Excel uploaded files on HHG FTP
ACTIONS
HHG completes print production per agreed upon workflow
HHG maintains tracker updated
OUTPUT
Printed/shipped files
TOOLS & SYSTEMS
Microsoft office TEAMs
Excel FTP
HHG FTP
HHG MCS

## Slide 15: REFERENCES

## Slide 16: Abbreviations
R&R | Recruitment and Retention
CLM | Country Lead Monitor
KOM | Kick Off Meeting
FTP | File Transfer Protocol
ERC | Ethics Review Committee
DTP | Desk Top Publishing
LMR | Legal, Medical, Regulatory

## Slide 17: English Core Localization Friendly Recommendations
Avoid terms or expressions that only apply in English (US)
Ensure names of games, apps, etc. are appropriate for local markets
Keep target audience in mind: formal and informal, gender-specific (when possible)
  (Example: avoid files that address both, children and adults. This causes grammatical issues and often extremely complicated and unnatural sentences due to many languages not only using different genders, but also formal and informal ways of addressing the readers)

## Slide 18: Bayer US LMR Guidance
Use of Mechanism of Action (MoA)
  Patient Facing pre consent materials: generally, not permissible to include information about compound mechanism of action as it could imply a known MoA for an investigational study
      Can include information about mechanism of disease
  Site facing materials: generally, more flexibility to include MoA information but must be done at the appropriate level
Use of Compound Name:
  Patient Facing pre consent materials: generally, not recommended to include the compound name. However, if referenced must include ‘investigational product in this population’ each time referenced
  Site facing materials: generally, more flexibility to include compound name. Conditional language ‘investigational product in this population’ may only be needed for initial reference.

## Slide 19: HHG Standard Specifications- Rate Card

## Slide 20: Footer Naming Convention
Placement: bottom of page, often last page only (follow placement of English core footer placed by R&R vendor)
2 footers should be included 1) English core and 2) country specific
The following convention should be utilized unless otherwise specified by Bayer R&R Manager
  Study Name & Alias (if available), Document Name, Country (Language), Version X.X, DDMMYY
    20275 Firefleye Next, Parent Booklet, English Core, Version 1.0, 20Feb20
    20275 Firefleye Next, Parent Booklet, Portugal (Portuguese), Version 1.0, 20Feb20
  China Only: Specifically for China, “country/region” needs to be differentiated as such, with corresponding language (Traditional Chinese or Simplified Chinese):
      China Mainland
      China
      Taiwan
      Hong Kong SAR
      Macau SAR
    Example: 20275 Firefleye Next, Parent Booklet, China Mainland (Simplified Chinese), Version 1, 20Feb20
Unless otherwise noted version number will only change if:
  English core footer-change to English core
  Country core footer-change after ERC submission

## Slide 21: File Naming Convention
File naming convention should be standard amongst all study vendors (R&R vendor, HHG and Excel) to ensure successful upload of the final print ready files to HHG FTP
Utilize the same country specific footer naming for file naming unless otherwise noted, eg:
    Footer Name:
      20275 Firefleye Next, Parent Booklet, English Core, Version 1.0, 20Feb20
      20275 Firefleye Next, Parent Booklet, Portugal (Portuguese), Version 1.0, 20Mar20
    File Name:
      20275 Firefleye Next_Parent Booklet_Portugal (Portuguese)_Version 1.0_20Mar20

## Slide 22: Document Setup for Printing
Crops and Bleeds (1/8” on both) for all printed documents
Footers should be included within crops and bleeds (areas to be printed) per naming convention (footer naming convention)
No information should be included inside the slug on any page of the documents
  Setting up the file in InDesign for print:
                Important Reminder:
                Bleed: refers to the image beyond the final trim that will be cut off after the material has been printed and cut down
                Crop marks: refers to the tick marks positioned on the corners of file that indicate final trim
                Safety Area: refers to the area inside the trim and is a smaller dimension than your final trim size and is important to pay attention to because this is where you should place your most important information within your design. Any content outside of the safe area is in risk of being cut off.
Only Settings Required for HHG

## Slide 23: HHG FTP & Pre-Flight

## Slide 24: Pre-Flight Checklist
It is encouraged to utilize the attached pre-flight checklist to ensure all activities are complete prior to submission. This form does not need to be submitted.

## Slide 25: Version History
Date of Roll Out | Revision Summary
09Mar22 | 1.) R&R Material Development, Bayer US LMR Guidance: Guidance from US LMR regarding content (MoA, Compound Name) 2.) Translation_US Spanish: Added clarification that Excel Translations will complete ICR of US Spanish and back-translation not needed
29Mar22 | 1.) Added note on cover slide ‘* Activities noted throughout this workflow for HHG also apply when another print vendor is utilized’ 2.) Pre- Flight, Pre- Flight 2: Added reference to Pre-Flight Checklist 3.) Pre-Flight Checklist: Added new pre-flight checklist tool

## Slide 26: Version History
Date of Roll Out | Revision Summary
30May20 | Initial version implementation
12Aug20 | Updated to include step 1.3 US LMR R&R Material Development: US LMR
22Sep20 | Added clarification on document setup for printing (Document Setup for Printing
29Sep20 | Added clarification to step 3.2 noting that Excel will follow the English design files as provided (Translation 3.2)
06Aug21 | 1.) R&R Material Development: Updated information regarding US LMR requirements 2.) Translation: Updated information regarding process for US/UK LMR Project number management
10Jan22 | English Core Localization Friendly Recommendations: Recommendations from Excel translations to support localization friendly content Document Setup for Printing: Added important note about bleeds, crop marks and safety areas