## Slide 1: Study Participant Feedback Survey Overview
///////////

## Slide 2: Content
Background
Tasks, Roles & Responsibilities
High Level Survey Implementation Overview
Support Documents
Patient Notification Thank You Card

## Slide 3: Background
New type of survey being supported by PRR Team team
Gain feedback from patients on their experience during the study
Gain insights and improve planning for future studies
Utilizes TransCelerate Patient Experience Toolkit
Survey is voluntary and anonymous
Implemented with limited study cost

## Slide 4: Overview of tasks (note some tasked may be completed in parallel)
Task | Considerations | Responsible | Timing | Budget
Survey Development | PRR will provide a set of draft questions for study team to review/modify and approve prior to beginning translations | PRR | 1 week | N/A
PIIC Consenting Language | PRR will provide generic language related to patient survey which can be included in PIIC PRR recommends that study team work directly with PIIC process owner (Katalin) | Study Team | 1-2 weeks | N/A
Patient Identification | Determine which patients will be contacted (all patients or only those who are still in the treatment phase, etc.) Develop speaking points for sites about the logistics for creating patient awareness about exit survey and consenting | Study Team PRR CLMs Sites | 1 week | N/A
Patient Notification Material | Develop patient facing material (sticker or card with a link/QR code which is unique per country) Once approved, PRR recommends providing asset to CLMs to print locally and distribute to participating sites | PRR | 1 week | N/A
Translations - PIIC | Assumes PIIC will be translated for all countries following standard PIIC process | StM SLM CLMs | TBC based on country | TBD based on country
Translations – Survey & Notification Material | Assumes survey and notification material will be translated for all countries CLM support will be needed to manage and sign off on translations in accordance with RD-SOP-1175 (share request at upcoming CLM meeting) | PRR SLM CLMs | 5-7 days | Global Translations Study Budget (for DTP)
EC Approvals | Final translated questionnaires will need to be submitted and approved by local EC | CLMs | TBC based on country | TBD based on country
Survey Programming in Qualtrics | Can be rolled-out as EC approvals are received | PRR | 2-3 Days | N/A

## Slide 5: High-level Survey Implementation Overview
Participant completes study ŧ (can be discontinuation, withdrawal or end of study)
Site provides patient with country specific survey notification material
Patient accesses survey via link/QR code from any mobile device/web and completes survey
Bayer will have access to real time survey responses (anonymized)
Ŧ Participant survey can be executed at various timepoints ( eg. start, middle, end of study) during the study. At a minimum the PRR team will plan to
execute at the end of the study (each patient completes) for the studies we support.

## Slide 6: Support documents
Item |  | Link
Questions | Draft survey questions [Reminder, no free text should be used due to translation needs for responses and to avoid any opportunity for AE/SAE reporting] | Generic Questions Library
PIIC language (sample text) | As you complete this study [can also use: Throughout this study], you may be asked to complete an online survey to collect feedback on your experience with participation in the clinical trial. Participation in this survey will be voluntary and anonymous. | N/A
Site support document | Guidance for sites on roll out of survey and speaking point to inform patients | Generic_Site Speaking Points
Patient Notification Tool | Editable pdf Thank you card with QR code/ link for patients | Thank you card_Survey Notification Tool
TranCelerate Patient Experience | Study Participant Feedback Questionnaire Toolkit | SPFQ Toolkit

## Slide 7: Patient Notification Thank You Card
The thank you card is provided to patients and includes a QR code/link to the survey
QR Code/link will be unique to each country and language